## Sheet1
步骤（同时也是分工） | Steps (also division of labor) | Person in charge（负责人）
1.用户研究（User Study）（你目前正在进行） 目标：理解大学生如何管理 学习、工作、社交、个人兴趣，以及他们在 Work-Life Balance (WLB) 方面遇到的问题。 📌 你应该做的 进行 访谈 / 焦点小组（已规划） 分析数据（编码分析，找出关键问题） 总结 关键痛点，形成 问题陈述（Problem Statement） 并写出此部分对应的报告内容，这应该是最终报告中的一部分！ 📄 需要写的报告部分： ✅ 方法（Methodology） 访谈的目标、研究方法（如“我们进行了 5 次半结构化访谈，了解大学生的时间管理模式”） 受访者信息（不涉及隐私，只写背景，如“受访者包括 3 名本科生和 2 名硕士生”） ✅ 结果（Findings） 访谈分析总结（如“我们发现 80% 的受访者表示难以平衡社交和学习”） 用户主要痛点 | 1.User Study (You are currently working on it) Objective: Understand how college students manage their study, work, socially, personal interests, and the problems they face in Work-Life Balance (WLB). 📌 What you should do Conduct Interviews / Focus Groups (Planned) Analyze data (coding analysis to identify key issues) Summary of key pain points, forming Problem Statement And write out the corresponding report content of this part, which should be part of the final report! 📄 Report section that needs to be written: ✅ Methodology Interview objectives and research methods (such as “We conducted 5 semi-structured interviews to understand the time management model of college students”) Respondent information (not involving privacy, only background is written, such as "respondents include 3 undergraduates and 2 masters") ✅ Results (Findings) Summary of interview analysis (such as “We found that 80% of respondents reported difficulty in balancing social and learning”) Main pain points for users | Yaohui Han deadline:3.14 16:30
2.定义问题（Problem Definition） 目标：根据用户研究，选定一个核心问题，明确“我们要解决什么问题”以及它的原因 & 影响。 📌 你应该做的 选出最值得解决的 WLB 问题（基于访谈分析） 撰写 清晰的问题陈述（Problem Statement） 例如： “大学生在管理学习和社交之间的平衡时，常常受到干扰，难以集中精力完成任务。我们希望设计一种数字技术来帮助他们高效管理学习时间，同时兼顾社交。” 并写出此部分对应的报告内容，这应该是最终报告中的一部分！ 设计目标（Design Goals） 📄 需要写的报告部分： ✅ 问题定义（Problem Definition） 主要问题的背景介绍 关键用户痛点（基于用户研究部分） 现有解决方案的不足（如“目前的时间管理应用过于复杂，用户不愿使用”） ✅ 设计目标（Design Goals） 你们的产品应该实现什么（如“设计一个简单直观的时间管理工具”） 约束条件（如“必须适应不同课程安排，易于使用”） | 2.Definition (Problem Definition) Objective: Based on user research, select a core problem and clarify "what problem we want to solve" and its reasons & impact. 📌 What you should do Select the most worthy WLB problem (based on interview analysis) Writing a clear statement of problem (Problem Statement) For example: “College students are often disrupted when managing the balance between learning and socializing and have difficulty concentrating on completing tasks. We want to design a digital technology to help them manage their learning time efficiently while taking into account socializing.” And write out the corresponding report content of this part, which should be part of the final report! 📄 Report section that needs to be written: ✅ Problem Definition Background introduction to the main issues Key user pain points (based on user research section) Inadequate solutions (such as “the current time management applications are too complex and users are reluctant to use them”) ✅ Design Goals What should your product achieve (such as "designing a simple and intuitive time management tool") Constraints (such as "must be adapted to different course arrangements and are easy to use") | Yang Song deadline: 3.15 16:30
3.头脑风暴 & 创意生成（Ideation） 目标：创造多种可能的解决方案，评估它们，并选择最有潜力的 2-3 个想法。 📌 你应该做的 团队讨论 & 头脑风暴： 产生尽可能多的创意解决方案 评估每个创意的优缺点 选择 2-3 个最佳设计方案（可以投票决定） 并写出此部分对应的报告内容（过程），这应该是最终报告中的一部分！ 📄 需要写的报告部分： ✅ 创意生成（Ideation） 头脑风暴的过程（可以列举 2-3 个未被采用的方案，并简述原因） ✅ 设计方案（Design Proposal） 最终方案的概述（如“我们设计了一款智能时间管理助手”） 功能描述（如“用户可以使用拖拽界面快速调整时间安排”） 交互逻辑（如“系统会自动推荐最优时间表”） | 3. Brainstorming & Creative Generation (Ideation) Objective: Create multiple possible solutions, evaluate them, and select the 2-3 ideas with the most potential. 📌 What you should do Team Discussion & Brainstorming: Generate as many creative solutions as possible Assess the pros and cons of each idea Choose 2-3 best designs (voting to decide) And write out the corresponding report content (process) for this part, which should be part of the final report! 📄 Report section that needs to be written: ✅ Creative Generation (Ideation) The process of brainstorming (can list 2-3 unused plans and briefly describe the reasons) ✅ Design Proposal Overview of the final solution (such as "We designed an intelligent time management assistant") Function description (such as "users can quickly adjust time schedules using the drag and drop interface") Interaction logic (such as "the system will automatically recommend the optimal timetable") | Wencheng Shi deadline: 3.16 16:30
4.设计 & 原型（Sketching & Prototyping） 目标：进一步完善选出的 2-3 个设计方案，创建草图、低保真原型（Lo-Fi Prototype），并让用户反馈。 📌 你应该做的 绘制设计草图（Sketching） 创建低保真原型（可以用 Figma、Balsamiq、手绘） 收集用户反馈（测试原型，看看是否符合需求） 最终选择一个最佳设计方案，作为视频原型的核心方案 并写出此部分对应的报告内容（过程），这应该是最终报告中的一部分！ 📄 需要写的报告部分： 界面草图 & 低保真原型的截图（可以用 Figma/手绘） ✅ 用户测试（User Testing） 访谈或可用性测试的反馈（如“用户表示交互界面清晰，但希望增加日程提醒功能”） 你们根据反馈调整的地方 | 4.Design & Prototyping Objective: Further improve the selected 2-3 design plans, create sketches, Lo-Fi Prototypes, and allow users to provide feedback. 📌 What you should do Draw a design sketch (sketching) Create a lo-fi prototype (can be used with Figma, Balsamiq, hand-painted) Collect user feedback (test prototype to see if it meets the requirements) Finally, choose the best design as the core solution for video prototypes And write out the corresponding report content (process) for this part, which should be part of the final report! 📄 Report section that needs to be written: Interface sketch & screenshots of the lo-fi prototype (can be hand-drawn with Figma/) ✅ User Testing Feedback from interviews or usability tests (such as "users indicate a clear interface but want to add a schedule reminder") What you adjusted based on feedback | Zeming Gao deadline:3.17 16:30
5.视频原型（Video Prototyping） 目标：制作一个 3 分钟的视频，清晰展示你的设计解决方案，包含问题背景 + 设计原型 + 解决方案。 📌 你应该做的 确定视频结构： 场景介绍（用户的问题） 你的解决方案（如何解决 WLB 问题） 产品功能演示 结论（为什么这个设计有效） 制作视频 你可以用 PowerPoint + 旁白，或用 Figma 交互原型录屏 也可以用简单动画工具（Canva, Vyond） 需要写的报告部分： ✅ 最终方案演示（Final Solution Presentation） 视频中的主要内容介绍 场景设计（如“第一幕：展示用户如何遇到 WLB 问题；第二幕：我们的产品如何帮助他们”） | 5. Video Prototyping Goal: Make a 3-minute video that clearly shows your design solution, including problem background + design prototype + solution. 📌 What you should do Determine the video structure: Scene introduction (user's question) Your solution (how to solve WLB problem) Product function demonstration Conclusion (Why this design works) Make a video You can use PowerPoint + narration, or use Figma to interact with the screen Simple animation tools (Canva, Vyond) can also be used Report section that needs to be written: ✅ Final Solution Presentation Introduction to the main content in the video Scene design (such as “Act 1: Show how users encounter WLB problems; Act 2: How our products help them”) | Jiaxin Cheng deadline: 3.18 16:30
6.设计报告（≤ 3000 字） -介绍 研究背景 -你的 用户研究方法 & 结果 -你的 问题陈述 -你的 创意生成过程（头脑风暴 + 选择的设计方案） -你的 草图、原型、用户反馈 -总结 & 未来改进方向 报告整合 & 编辑（Final Editing） 📌 负责内容： 汇总各个部分 统一格式、语气、写作风格 检查语法、拼写、引用格式 | 6.Design report (≤ 3000 words)() -Introduction Research Background -Your User Research Methods & Results -Your Problem Statement - Your creative generation process (brainstorm + selected design plan) -Your sketch, prototype, user feedback -Summary & Future Improvement Directions Report Integration & Editing 📌 Responsible for content: Summary of various parts Unified format, tone, writing style Check grammar, spelling, quotation format | Gloris deadline: 3.20 16:30